## Yr 1-2 Programme
Colchester School Neighbourhood (Delivery Programme)
Trial Window
Task |  | Key Dates | Lead Person | RAG | Notes | April | May | June | July | August | September | October | November | December | January | February | March
Year 1:
Project Set-up & Governance | Inception Meeting with ECC and site visit |  | RW | bar: May
Recruitment & Staff Training: (Willow)
| Recruit Engagement Officer |  | RW | bar: April to May
| Engagement Officer Start Date (RW to cover role prior to start date) |  | RW | bar: June
| Engagement Officer Induction/Training tailored to the requirements of the project |  | RW | bar: July; September
Project Documentation & Methodology:
| Develop Communications Plan, and then deliver throughout the project including press releases, social media, posters leaflets etc. |  | RW |  | Completed by MJ | bar: April; June to July; Trial Window October
| Develop Monitoring Framework, including liaison with RMU |  | MJ | bar: April
| Design Engagement Process Methodology |  | MJ | bar: April
| Obtain CAD base plans from ECC |  | MJ | bar: April
Research/Monitoring & Engagement Resources:
| Research and analyse existing initiatives, strategies etc. |  | RW |  | MJ to support analysis of built environment information | bar: April to May
| Appoint Streets Systems fro camera monitoring |  | MJ | bar: April
| Collected baseline camera monitoring information with Streets Systems | 2019-11-11 | MJ |  | Review after stage 1 engagement analysis | bar: Trial Window November
| Purchase materials for pop-up engagement events, and prepare supporting documents such as sign in sheets. |  | RW |  | Completed by WM | bar: June
| Set-up on-line mapping system/survey |  | MJ | bar: April
| Purchase Street kit and organise storage | 2019-09-30 | MJ |  | All orders placed, firming up school storage arrangements WM | bar: July; September
Initial Contact with Stakeholders and Delivery Partners:
| Presentation of potential changes to Highways Team to flag early concerns, information requirements. |  | MJ |  | Presentation at ECC Design Forum workshop & on-site meeting with Vicky Duff | bar: June to July
| Identification and initial meetings with stakeholders (Including schools, Ward Councillors, Local Businesses etc.) -Provide opportunity to review and shape planned engagement approach - Stakeholder mapping |  | RW |  | Carried out by WM, and will be on-going during project delivery | bar: May to June; September
Project Governance:
| Establish governance structure (including project panel and Working Groups). Attend steering group meetings and project meetings |  | RW |  | MJ worked with HA to confirm structure | bar: August to September
| Define scoring/cost benefit matrix with ECC |  | MJ |  | Scoring table used as part of W1 trials CBA to be confirmed by ECC | bar: July to August
| ECC Catch-ups & Reporting Weekly catch-ups are conducted via Skype with ECC and a meeting/reporting schedule has been agreed: |  | RW/WM |  | Established and structured by MJ with support from WM (August report is drafted) | bar: September; Trial Window November; Trial Window March
School Hubs: Fiveways Primary School, Stanway Secondary, Stanway Primary School
Raising Awareness | Phase 1: Raising Awareness, Engagement & Pop-ups: Engage all stakeholders including businesses within the catchment of the hubs to establish aspirations/concerns key active travel routes. -Recruit Project Champions -Deliver survey including on-line version - Eye catching activities to support the Pop-ups | Both phases need to be completed prior to summer holidays | RW |  | Delivered by WM with support from RW/MJ | bar: June to July
| Phase 2: Workshop Design Development: Planning for Real workshops to map aspirations/concerns/active travel routes and develop initial design ideas. Workshops to be delivered to all stakeholders in the hubs catchment. - Mapping will also be made available on-line |  | MJ |  | Materials provided by MJ and workshops delivered by WM | bar: June to July
| Analysis of findings from Phase 1-2 translated into August report and use to develop trial layout plans. |  | MJ |  | Analysis and inputting carried out by MJ/WM | bar: August
Empowering Change | Produce RA's and supporting plans for trial delivery, and liaise with delivery partners. |  | MJ |  | MM to support this element with Highway Engineering expertise | bar: August to September
| Street kit trial permissions: Approval from Steering Group, Essex Highways, which will require supporting layout plans and assessment matrix |  | MJ |  | MM to support this element with Highway Engineering expertise | bar: September
Street Kit Trials & Events
| Survey materials and Monitoring arrangements put in place |  | MJ | bar: September to Trial Window October
| Monitoring of trials using go-pro camera and in-house heat map approach. |  | MJ |  | Street Systems are able to do this as part of there current commission value
| Trials set-up on Winstree Road using street kit |  | MJ |  | WM to support set-up delivery and potential involvement of champions | bar: Trial Window October to Trial Window November
| Deliver on-street activities to support street kit installation period and feedback findings from Phases 1-2including how they have informed the trial |  | WM |  | Activities to help promote the potential of the street that can be unlocked | bar: Trial Window October to Trial Window November
| Collect feedback on trial ideas via on street/on-line surveys and voting. |  | WM | bar: Trial Window October to Trial Window November
School Hub: Lexden Springs (Special School) Opens September 2019
Raising Awareness | Establish links with Lexden Springs to embed them into the project process, and link the project with the schools opening. Raise Awareness with wider SS pupil community following yr7 engagement. |  | WM |  | MJ to support these events (support while PO is recruited) | bar: September
| Deliver workshop/s with the school which connects the pupils with the pop-up engagement we are doing in this location. Due to the change of dynamic in this location with the schools opening, a trial is not going to be delivered. However during the trial window engagement will be carried out in this location using the large comments mapping. |  | WM | bar: Trial Window November
Schools Connected with Trials and Key Routes: (Scope for project champions to be involved)
Empowering Change | Workshop 1 – Connecting Schools with Trials: Workshop which connects each school (with the exception of Lexden) with there nearest street trial, and gains feedback on the concept designs. |  | WM |  | There is flexibility to combine these workshops into one session depending on time/structure of the session the schools can offer. | bar: Trial Window October to Trial Window November
| Workshop 2 – Key Routes/Park and Stride: This workshop will develop the park and stride element of the project, linking it with key active travel routes and identifying opportunities and barriers. |  | WM | bar: Trial Window October to Trial Window November
Year 2: | [5 empty] | Trial Window October: Trial Window
Task |  | Key Dates | Lead Person | RAG | Notes | April | May | June | July | August | September | October | November | December | January | February | March
New Officer & C19 Planning Requirements | Recruitment & Staff Training: (Gillian)
| Recruit Engagement Officer |  | MJ | bar: April
| Engagement Officer Start Date | 2020-03-30 | MJ | bar: April
| Engagement Officer Induction/Training tailored to the requirements of the project |  | MJ |  | MJ Supporting GL to arrange training within restraints of C19 | bar: April to June
Project Documentation & Methodology: (C19 Revisions)
| Refresh and deliver communications plan exploring the role of social media to promote the project in response to C19 restrictions and opportunities |  | GL | bar: April to May
| Monitoring Framework, updated to reflect C19 changes in engagement and trial delivery. |  | MJ |  | MJ to Liaise with RMU and Street Systems | bar: April
| Refresh engagement methodology looking at opportunities and the role of on-line engagement in response to C19. |  | GL | bar: April
| Liaise with key project stakeholders to introduce Gillian and gain support for the revised engagement approach. |  | GL |  | As part of the initial contact with schools a new schools representative will be investigated | bar: April to May
Raising Awareness | Year 1 Feedback & Additional Community Engagement: (Working Within C19 Restrictions/Opportunities)
| Window 1 Trial feedback & Year 2 Delivery: Project Team Reporting: The findings and voting results from the window 1 trials will be presented to the project team. How these findings shape year 2 delivery along with C19 considerations will also be presented. Stakeholder Newsletter: Update since the last trials, introducing online engagement and adjustments in response to C 19 |  | MJ |  | GL will support MJ to produce the project reporting materials, and will lead on the stakeholder update Newsletter | bar: May
| Online Engagement: (Trial refinement & behaviour change) Introduce the plans for the trials, gain community feedback, suggestions and comments. Online questionnaire: To help understand opinions on the first trial but also to understand why modes of transport are chosen – this will help shape the behaviour change messaging later in the year. Online schools engagement: Online activities which link to the main engagement. This could include, lessons to help them understand the engagement and linking to the main online mapping tool / questionnaire. |  | GL | bar: May to June
| Street Pop-ups & Street Party (Restrictions Lifted) The role of this stage is to connect with stakeholders face to face if restrictions are lifted Pop-ups around the area to gather feedback on the previous and planned trials. Street party purpose to gain feedback but can also be an opportunity to offer services which may help behaviour change such as Dr Bike, bike safety information, health benefit info. |  | GL
| Street Pop-ups & Street Party (Restrictions Not Lifted) July is a continuation of the online engagement – to evolve depending on response rates and general feedback and the street pop ups are removed. Targeted engagement with key stakeholder groups, perhaps creation of forums held using Zoom / Skype or similar. Street party moves to early September and is branded as a ‘Big Launch Event’ for the trials and can be used to make sure people know about what is going on. |  | GL | bar: July
Taking Action | Trial Delivery:
| Trial Designs & Permissions: Approval from Steering Group including Essex Highways, which will require supporting layout plans RA's and assessment matrix. Materials to be used during trials to transfer designs onto the ground. Street kits will be utilised as well as other fast and light materials such as temporary paint, planters. |  | MJ | bar: August
| Mobilising for trial delivery: Orders placed for materials, and support/organisation put in place from other Sustrans teams (London)/community to install the trials. Traffic management permissions, and measures organised |  | MJ | bar: August to September
| Ensure monitoring and survey materials are in place for the window 2 trials. |  | MJ | bar: August to Trial Window October
| Behaviour change / Preparation for the trials: Very light touch, GL using on-line platforms to raise awareness of the trials. Walk or bike to school challenge: (Linked with park & stride) This is designed to help encourage behaviour change, will start in advance of the trails so that people have time to prepare. This could be things like nature trails, mindful walking etc. Could combine with a classroom activity. |  | GL | bar: September to Trial Window October
Trial Delivery (window 2)
| Trials set-up on Winstree Road using street kit and additional materials to support types of trials. |  | MJ |  | GL to support set-up delivery and potential involvement of champions | bar: Trial Window October
| On-Line Engagement to maximise impact of trials and to gauge opinion using survey |  | GL | bar: Trial Window October
| Monitoring: Street Systems to carryout video monitoring to gauge impact of trials. |  | MJ | bar: Trial Window October
Trial Decommissioning & Analysis:
| Removal of trial elements including transfer to schools: Trials to be decommissioned, and materials transferred to schools or if possible left in place with ECC permission. |  | GL | bar: Trial Window November
| Analysis: Analysis of monitoring findings in relation to baseline, and community feedback survey. |  | MJ | bar: Trial Window December to Trial Window January
| Concept Designs: Amendments to concept designs (in CAD) resulting from trials, which will provide a longer term vision for Winstree Road. |  | MJ |  | Senior Engineer to support the delivery of these elements | bar: Trial Window February
Project Legacy | Legacy Activities:
| Project Newsletter: Thanking those who participated in the trials, explain the mechanisms for feedback and generally tell a positive story of the trials. |  | GL | bar: Trial Window December
Final Project Reporting, Workshop & Handover:
| Project monitoring incorporated into final report |  | MJ | bar: Trial Window January to Trial Window February
| Final project report capturing project findings and recommendations |  | MJ | bar: Trial Window January to Trial Window February
| Presentation & Workshop: Report and recommendations presented to project partners including workshop: -To explore next steps for Winstree Rd capital delivery -Identify other locations where the Winstree Rd approach is needed. |  | MJ | bar: Trial Window February to Trial Window March